## README
Campaign Playbook Import Format — Specification
Schema version | 1
Issue | https://github.com/GHolmesDesigns/hybrid-command-center/issues/17
Deliverable | XLSX authoring and import contract; this workbook is a spec and example, not an importer.
Purpose | Create clients, projects, tasks, checklist items, and task dependencies in one confirmed action.
Workbook structure
Required data tabs | Clients, Projects, Tasks, ChecklistItems. Dependencies is optional and may be empty.
Metadata tabs | README, DataDictionary, and AllowedValues are documentation and are ignored by the importer.
Hierarchy | Client → Project → Task → ChecklistItem; Dependencies links a task to another task prerequisite.
Rationale | Separate hierarchy tabs avoid repeated parent metadata and make row-level validation and references explicit.
Authoring contract
Headers | Sheet names and column headers are exact and case-sensitive. Unknown data tabs or columns are rejected.
Cell values | Literal values only. Formulas, macros, merged data cells, and hidden data are rejected.
Blank rows | Fully blank rows are ignored. Partially populated rows are reported as validation errors.
Dates | Literal YYYY-MM-DD calendar dates; no timezone conversion and no Excel/Sheets date serials.
Keys | Required workbook-local identifiers, trimmed, case-sensitive, 1–64 characters, pattern [A-Z][A-Z0-9_-]*.
Uniqueness | client_key, project_key, and task_key are unique within their defining tabs. References must match exactly.
Ordering | Workbook order values are positive 1-based integers. Duplicates are errors; gaps are allowed and normalized on import.
Ordering scope | Project position is workbook-wide; Task position is per project and status; item_order is per task.
Enums | Use only the exact uppercase values shown on AllowedValues. Blank optional fields use documented defaults.
Conflict behavior — create-only v1
Client conflict | An existing client with the same trimmed name, compared case-insensitively.
Project conflict | An existing project under the resolved client with the same trimmed name, compared case-insensitively.
Task conflict | An existing task under the resolved project with the same trimmed title, compared case-insensitively.
Archived records | Archived clients/projects still count as conflicts and are reported; they are never silently reused.
Repeated import | Re-importing the same workbook is refused through the same natural-key checks; no merge or duplicate is implicit.
Validation, preview, and commit
Preview | Show create counts by tab plus every cell error, duplicate, unresolved reference, cycle, and existing-record conflict.
Confirmation | Confirmation is enabled only for a clean preview. Nothing is written from a preview containing any error.
Atomic write | After confirmation, all SQLite inserts occur in one transaction; any database failure rolls back the entire import.
Completion time | A task imported as COMPLETE receives completed_at equal to the confirmation timestamp.
Drive safety | The transaction creates local records only. Client/project Drive provisioning begins afterward as retry-safe PENDING work.
Drive boundaries | Import never renames, moves, deletes, or overwrites existing Drive files or folders.
Dependencies and templates
Dependency rules | Both keys must resolve to Tasks rows. Self-links, duplicate pairs, and cycles are errors. Cross-project links are allowed.
Task types | Canonical vocabulary is the completed issue #11 vocabulary listed on AllowedValues.
Checklist/template rule | Imported ChecklistItems are authoritative. If a task has any, import exactly them and do not seed issue #16 defaults.
Template fallback | If a task has no imported checklist rows, the issue #16 static template may seed defaults from task_type.
Examples
Six Weeks of Clarity | Rows fully enumerate the real six-week cadence: 60 tasks, their ordered checklist items, and within-week dependencies.
AdDrive Media | Rows show a deliverable-based client engagement rather than a weekly recurring campaign.
Example colors | Blue rows belong to Six Weeks of Clarity; pink rows belong to AdDrive Media. Color is documentary only.
Acceptance note | The workbook defines the executable contract. A production importer must validate raw cell values, not formatting.

## Clients
client_key | name | contact_name | email | phone | website | notes | client_import_source | client_import_id
CLI-GHD | G.Holmes Designs (studio-owned) |  |  |  | https://www.gholmesdesigns.com | Studio-owned campaigns use a real client record; no null-client special case. | 9d3f1c62-5a47-4e8b-b0d2-7c6841ae5f30 | ghd-studio
CLI-ADDRIVE | AdDrive Media Engagement LLC |  |  | 850-251-5465 |  | Tallahassee-based measured vehicle-wrap advertising company (mobility OOH). Address: 2330 Centerville Road, Tallahassee, FL 32303. | 9d3f1c62-5a47-4e8b-b0d2-7c6841ae5f30 | addrive-media

## Projects
project_key | client_key | name | status | priority | start_date | target_deadline | description | notes | position
PRJ-6WOC | CLI-GHD | Six Weeks of Clarity | ACTIVE | URGENT |  |  | Custom whiteboard explainer campaign built around a six-week content cadence. | The example fully enumerates all six weekly task groups, checklist items, and within-week dependencies. | 1
PRJ-ADDRIVE-BRAND | CLI-ADDRIVE | AdDrive Media — Brand Refresh, Website & Recruitment | ACTIVE | URGENT |  |  | Website, brand refresh, content, photography, illustration, video, social media, paid campaign, and driver-recruitment work. | Approved language emphasizes vehicle-wrap advertising, mobility OOH, GPS tracking, route data, monthly reporting, and Event SURGE. | 2

## Tasks
task_key | project_key | title | task_type | status | priority | start_date | due_date | description | notes | position
TSK-001 | PRJ-6WOC | Week 1 blog post | BLOG_POST | COMPLETE | HIGH |  |  | Draft, edit, and deliver the post as Markdown for Week 1's clarity theme. |  | 1
TSK-002 | PRJ-6WOC | Week 1 whiteboard video segment | VIDEO | COMPLETE | URGENT |  |  | Produce the Week 1 segment from script through animation. |  | 2
TSK-003 | PRJ-6WOC | Week 1 social post set | SOCIAL_POST | COMPLETE | HIGH |  |  | Prepare Week 1 platform captions, check voice, use #ThinkVisually where appropriate, and use no emoji. |  | 3
TSK-004 | PRJ-6WOC | Week 1 graphics set | GRAPHICS | COMPLETE | HIGH |  |  | Create Week 1 thumbnails, quote cards, and carousel assets in the brand palette with the registration-mark motif. |  | 4
TSK-005 | PRJ-6WOC | Schedule Week 1 blog post | SCHEDULING | COMPLETE | HIGH |  |  | Schedule the Week 1 blog post on gholmesdesigns.com. |  | 5
TSK-006 | PRJ-6WOC | Schedule Week 1 social posts | SCHEDULING | COMPLETE | HIGH |  |  | Queue Week 1 platform posts. |  | 6
TSK-007 | PRJ-6WOC | Cross-link Week 1 campaign content | SCHEDULING | COMPLETE | MEDIUM |  |  | Link Week 1 social copy to the blog/video and the blog to the video. |  | 7
TSK-008 | PRJ-6WOC | Week 1 brand review | QA_BRAND_PASS | COMPLETE | HIGH |  |  | Check Week 1 typefaces, palette, gradients, mascots, and visual clichés. |  | 8
TSK-009 | PRJ-6WOC | Week 1 performance snapshot | ADMIN | COMPLETE | MEDIUM |  |  | Pull the platform-native performance snapshot available for the Week 1 review. |  | 9
TSK-010 | PRJ-6WOC | Prepare Week 2 brief | ADMIN | COMPLETE | MEDIUM |  |  | Record the topic, hook, and format carrying into the Week 2 brief. |  | 10
TSK-011 | PRJ-6WOC | Week 2 blog post | BLOG_POST | BACKLOG | HIGH |  |  | Draft, edit, and deliver the post as Markdown for Week 2's clarity theme. |  | 1
TSK-012 | PRJ-6WOC | Week 2 whiteboard video segment | VIDEO | BACKLOG | URGENT |  |  | Produce the Week 2 segment from script through animation. |  | 2
TSK-013 | PRJ-6WOC | Week 2 social post set | SOCIAL_POST | BACKLOG | HIGH |  |  | Prepare Week 2 platform captions, check voice, use #ThinkVisually where appropriate, and use no emoji. |  | 3
TSK-014 | PRJ-6WOC | Week 2 graphics set | GRAPHICS | BACKLOG | HIGH |  |  | Create Week 2 thumbnails, quote cards, and carousel assets in the brand palette with the registration-mark motif. |  | 4
TSK-015 | PRJ-6WOC | Schedule Week 2 blog post | SCHEDULING | BACKLOG | HIGH |  |  | Schedule the Week 2 blog post on gholmesdesigns.com. |  | 5
TSK-016 | PRJ-6WOC | Schedule Week 2 social posts | SCHEDULING | BACKLOG | HIGH |  |  | Queue Week 2 platform posts. |  | 6
TSK-017 | PRJ-6WOC | Cross-link Week 2 campaign content | SCHEDULING | BACKLOG | MEDIUM |  |  | Link Week 2 social copy to the blog/video and the blog to the video. |  | 7
TSK-018 | PRJ-6WOC | Week 2 brand review | QA_BRAND_PASS | BACKLOG | HIGH |  |  | Check Week 2 typefaces, palette, gradients, mascots, and visual clichés. |  | 8
TSK-019 | PRJ-6WOC | Week 2 performance snapshot | ADMIN | BACKLOG | MEDIUM |  |  | Pull the platform-native performance snapshot available for the Week 2 review. |  | 9
TSK-020 | PRJ-6WOC | Prepare Week 3 brief | ADMIN | BACKLOG | MEDIUM |  |  | Record the topic, hook, and format carrying into the Week 3 brief. |  | 10
TSK-021 | PRJ-6WOC | Week 3 blog post | BLOG_POST | BACKLOG | HIGH |  |  | Draft, edit, and deliver the post as Markdown for Week 3's clarity theme. |  | 11
TSK-022 | PRJ-6WOC | Week 3 whiteboard video segment | VIDEO | BACKLOG | URGENT |  |  | Produce the Week 3 segment from script through animation. |  | 12
TSK-023 | PRJ-6WOC | Week 3 social post set | SOCIAL_POST | BACKLOG | HIGH |  |  | Prepare Week 3 platform captions, check voice, use #ThinkVisually where appropriate, and use no emoji. |  | 13
TSK-024 | PRJ-6WOC | Week 3 graphics set | GRAPHICS | BACKLOG | HIGH |  |  | Create Week 3 thumbnails, quote cards, and carousel assets in the brand palette with the registration-mark motif. |  | 14
TSK-025 | PRJ-6WOC | Schedule Week 3 blog post | SCHEDULING | BACKLOG | HIGH |  |  | Schedule the Week 3 blog post on gholmesdesigns.com. |  | 15
TSK-026 | PRJ-6WOC | Schedule Week 3 social posts | SCHEDULING | BACKLOG | HIGH |  |  | Queue Week 3 platform posts. |  | 16
TSK-027 | PRJ-6WOC | Cross-link Week 3 campaign content | SCHEDULING | BACKLOG | MEDIUM |  |  | Link Week 3 social copy to the blog/video and the blog to the video. |  | 17
TSK-028 | PRJ-6WOC | Week 3 brand review | QA_BRAND_PASS | BACKLOG | HIGH |  |  | Check Week 3 typefaces, palette, gradients, mascots, and visual clichés. |  | 18
TSK-029 | PRJ-6WOC | Week 3 performance snapshot | ADMIN | BACKLOG | MEDIUM |  |  | Pull the platform-native performance snapshot available for the Week 3 review. |  | 19
TSK-030 | PRJ-6WOC | Prepare Week 4 brief | ADMIN | BACKLOG | MEDIUM |  |  | Record the topic, hook, and format carrying into the Week 4 brief. |  | 20
TSK-031 | PRJ-6WOC | Week 4 blog post | BLOG_POST | BACKLOG | HIGH |  |  | Draft, edit, and deliver the post as Markdown for Week 4's clarity theme. |  | 21
TSK-032 | PRJ-6WOC | Week 4 whiteboard video segment | VIDEO | BACKLOG | URGENT |  |  | Produce the Week 4 segment from script through animation. |  | 22
TSK-033 | PRJ-6WOC | Week 4 social post set | SOCIAL_POST | BACKLOG | HIGH |  |  | Prepare Week 4 platform captions, check voice, use #ThinkVisually where appropriate, and use no emoji. |  | 23
TSK-034 | PRJ-6WOC | Week 4 graphics set | GRAPHICS | BACKLOG | HIGH |  |  | Create Week 4 thumbnails, quote cards, and carousel assets in the brand palette with the registration-mark motif. |  | 24
TSK-035 | PRJ-6WOC | Schedule Week 4 blog post | SCHEDULING | BACKLOG | HIGH |  |  | Schedule the Week 4 blog post on gholmesdesigns.com. |  | 25
TSK-036 | PRJ-6WOC | Schedule Week 4 social posts | SCHEDULING | BACKLOG | HIGH |  |  | Queue Week 4 platform posts. |  | 26
TSK-037 | PRJ-6WOC | Cross-link Week 4 campaign content | SCHEDULING | BACKLOG | MEDIUM |  |  | Link Week 4 social copy to the blog/video and the blog to the video. |  | 27
TSK-038 | PRJ-6WOC | Week 4 brand review | QA_BRAND_PASS | BACKLOG | HIGH |  |  | Check Week 4 typefaces, palette, gradients, mascots, and visual clichés. |  | 28
TSK-039 | PRJ-6WOC | Week 4 performance snapshot | ADMIN | BACKLOG | MEDIUM |  |  | Pull the platform-native performance snapshot available for the Week 4 review. |  | 29
TSK-040 | PRJ-6WOC | Prepare Week 5 brief | ADMIN | BACKLOG | MEDIUM |  |  | Record the topic, hook, and format carrying into the Week 5 brief. |  | 30
TSK-041 | PRJ-6WOC | Week 5 blog post | BLOG_POST | BACKLOG | HIGH |  |  | Draft, edit, and deliver the post as Markdown for Week 5's clarity theme. |  | 31
TSK-042 | PRJ-6WOC | Week 5 whiteboard video segment | VIDEO | BACKLOG | URGENT |  |  | Produce the Week 5 segment from script through animation. |  | 32
TSK-043 | PRJ-6WOC | Week 5 social post set | SOCIAL_POST | BACKLOG | HIGH |  |  | Prepare Week 5 platform captions, check voice, use #ThinkVisually where appropriate, and use no emoji. |  | 33
TSK-044 | PRJ-6WOC | Week 5 graphics set | GRAPHICS | BACKLOG | HIGH |  |  | Create Week 5 thumbnails, quote cards, and carousel assets in the brand palette with the registration-mark motif. |  | 34
TSK-045 | PRJ-6WOC | Schedule Week 5 blog post | SCHEDULING | BACKLOG | HIGH |  |  | Schedule the Week 5 blog post on gholmesdesigns.com. |  | 35
TSK-046 | PRJ-6WOC | Schedule Week 5 social posts | SCHEDULING | BACKLOG | HIGH |  |  | Queue Week 5 platform posts. |  | 36
TSK-047 | PRJ-6WOC | Cross-link Week 5 campaign content | SCHEDULING | BACKLOG | MEDIUM |  |  | Link Week 5 social copy to the blog/video and the blog to the video. |  | 37
TSK-048 | PRJ-6WOC | Week 5 brand review | QA_BRAND_PASS | BACKLOG | HIGH |  |  | Check Week 5 typefaces, palette, gradients, mascots, and visual clichés. |  | 38
TSK-049 | PRJ-6WOC | Week 5 performance snapshot | ADMIN | BACKLOG | MEDIUM |  |  | Pull the platform-native performance snapshot available for the Week 5 review. |  | 39
TSK-050 | PRJ-6WOC | Prepare Week 6 brief | ADMIN | BACKLOG | MEDIUM |  |  | Record the topic, hook, and format carrying into the Week 6 brief. |  | 40
TSK-051 | PRJ-6WOC | Week 6 blog post | BLOG_POST | BACKLOG | HIGH |  |  | Draft, edit, and deliver the post as Markdown for Week 6's clarity theme. |  | 41
TSK-052 | PRJ-6WOC | Week 6 whiteboard video segment | VIDEO | BACKLOG | URGENT |  |  | Produce the Week 6 segment from script through animation. |  | 42
TSK-053 | PRJ-6WOC | Week 6 social post set | SOCIAL_POST | BACKLOG | HIGH |  |  | Prepare Week 6 platform captions, check voice, use #ThinkVisually where appropriate, and use no emoji. |  | 43
TSK-054 | PRJ-6WOC | Week 6 graphics set | GRAPHICS | BACKLOG | HIGH |  |  | Create Week 6 thumbnails, quote cards, and carousel assets in the brand palette with the registration-mark motif. |  | 44
TSK-055 | PRJ-6WOC | Schedule Week 6 blog post | SCHEDULING | BACKLOG | HIGH |  |  | Schedule the Week 6 blog post on gholmesdesigns.com. |  | 45
TSK-056 | PRJ-6WOC | Schedule Week 6 social posts | SCHEDULING | BACKLOG | HIGH |  |  | Queue Week 6 platform posts. |  | 46
TSK-057 | PRJ-6WOC | Cross-link Week 6 campaign content | SCHEDULING | BACKLOG | MEDIUM |  |  | Link Week 6 social copy to the blog/video and the blog to the video. |  | 47
TSK-058 | PRJ-6WOC | Week 6 brand review | QA_BRAND_PASS | BACKLOG | HIGH |  |  | Check Week 6 typefaces, palette, gradients, mascots, and visual clichés. |  | 48
TSK-059 | PRJ-6WOC | Week 6 performance snapshot | ADMIN | BACKLOG | MEDIUM |  |  | Pull the platform-native performance snapshot available for the Week 6 review. |  | 49
TSK-060 | PRJ-6WOC | Capture final campaign learnings | ADMIN | BACKLOG | MEDIUM |  |  | Record final campaign learnings and next-campaign recommendations. |  | 50
TSK-101 | PRJ-ADDRIVE-BRAND | Flagship explainer v2 revision | VIDEO | COMPLETE | URGENT |  |  | Revise claims, closing tagline, driver terminology, and CTA copy. |  | 1
TSK-102 | PRJ-ADDRIVE-BRAND | Website and inquiry forms | OTHER | IN_PROGRESS | URGENT |  |  | Maintain the client-facing site and confirm driver and brand inquiry collection. |  | 2
TSK-103 | PRJ-ADDRIVE-BRAND | Tallahassee driver-recruitment Meta ads | OTHER | IN_PROGRESS | URGENT |  |  | Run and monitor the driver-recruitment campaign for the Tallahassee market. |  | 3
TSK-104 | PRJ-ADDRIVE-BRAND | Weekly blog and social draft cycle | BLOG_POST | IN_PROGRESS | HIGH |  |  | Generate weekly blog and social drafts and route them for review. |  | 4

## ChecklistItems
task_key | item_order | title | completed
TSK-001 | 1 | Draft | TRUE
TSK-001 | 2 | Edit | TRUE
TSK-001 | 3 | Deliver as Markdown | TRUE
TSK-002 | 1 | Script | TRUE
TSK-002 | 2 | Storyboard | TRUE
TSK-002 | 3 | InstaDoodle illustration | TRUE
TSK-002 | 4 | Animation | TRUE
TSK-003 | 1 | Draft platform-specific captions | TRUE
TSK-003 | 2 | Check brand voice | TRUE
TSK-003 | 3 | Confirm #ThinkVisually where appropriate and no emoji | TRUE
TSK-004 | 1 | Create thumbnails | TRUE
TSK-004 | 2 | Create quote cards | TRUE
TSK-004 | 3 | Create carousel assets | TRUE
TSK-004 | 4 | Verify CMYK palette and registration-mark motif | TRUE
TSK-005 | 1 | Schedule on gholmesdesigns.com | TRUE
TSK-006 | 1 | Queue platform posts | TRUE
TSK-007 | 1 | Link social copy to blog or video | TRUE
TSK-007 | 2 | Link blog to video | TRUE
TSK-008 | 1 | Verify approved typefaces and palette | TRUE
TSK-008 | 2 | Confirm no gradients or mascots | TRUE
TSK-008 | 3 | Confirm no visual clichés | TRUE
TSK-009 | 1 | Pull prior-week native analytics | TRUE
TSK-010 | 1 | Record topic, hook, and format for next brief | TRUE
TSK-011 | 1 | Draft | FALSE
TSK-011 | 2 | Edit | FALSE
TSK-011 | 3 | Deliver as Markdown | FALSE
TSK-012 | 1 | Script | FALSE
TSK-012 | 2 | Storyboard | FALSE
TSK-012 | 3 | InstaDoodle illustration | FALSE
TSK-012 | 4 | Animation | FALSE
TSK-013 | 1 | Draft platform-specific captions | FALSE
TSK-013 | 2 | Check brand voice | FALSE
TSK-013 | 3 | Confirm #ThinkVisually where appropriate and no emoji | FALSE
TSK-014 | 1 | Create thumbnails | FALSE
TSK-014 | 2 | Create quote cards | FALSE
TSK-014 | 3 | Create carousel assets | FALSE
TSK-014 | 4 | Verify CMYK palette and registration-mark motif | FALSE
TSK-015 | 1 | Schedule on gholmesdesigns.com | FALSE
TSK-016 | 1 | Queue platform posts | FALSE
TSK-017 | 1 | Link social copy to blog or video | FALSE
TSK-017 | 2 | Link blog to video | FALSE
TSK-018 | 1 | Verify approved typefaces and palette | FALSE
TSK-018 | 2 | Confirm no gradients or mascots | FALSE
TSK-018 | 3 | Confirm no visual clichés | FALSE
TSK-019 | 1 | Pull prior-week native analytics | FALSE
TSK-020 | 1 | Record topic, hook, and format for next brief | FALSE
TSK-021 | 1 | Draft | FALSE
TSK-021 | 2 | Edit | FALSE
TSK-021 | 3 | Deliver as Markdown | FALSE
TSK-022 | 1 | Script | FALSE
TSK-022 | 2 | Storyboard | FALSE
TSK-022 | 3 | InstaDoodle illustration | FALSE
TSK-022 | 4 | Animation | FALSE
TSK-023 | 1 | Draft platform-specific captions | FALSE
TSK-023 | 2 | Check brand voice | FALSE
TSK-023 | 3 | Confirm #ThinkVisually where appropriate and no emoji | FALSE
TSK-024 | 1 | Create thumbnails | FALSE
TSK-024 | 2 | Create quote cards | FALSE
TSK-024 | 3 | Create carousel assets | FALSE
TSK-024 | 4 | Verify CMYK palette and registration-mark motif | FALSE
TSK-025 | 1 | Schedule on gholmesdesigns.com | FALSE
TSK-026 | 1 | Queue platform posts | FALSE
TSK-027 | 1 | Link social copy to blog or video | FALSE
TSK-027 | 2 | Link blog to video | FALSE
TSK-028 | 1 | Verify approved typefaces and palette | FALSE
TSK-028 | 2 | Confirm no gradients or mascots | FALSE
TSK-028 | 3 | Confirm no visual clichés | FALSE
TSK-029 | 1 | Pull prior-week native analytics | FALSE
TSK-030 | 1 | Record topic, hook, and format for next brief | FALSE
TSK-031 | 1 | Draft | FALSE
TSK-031 | 2 | Edit | FALSE
TSK-031 | 3 | Deliver as Markdown | FALSE
TSK-032 | 1 | Script | FALSE
TSK-032 | 2 | Storyboard | FALSE
TSK-032 | 3 | InstaDoodle illustration | FALSE
TSK-032 | 4 | Animation | FALSE
TSK-033 | 1 | Draft platform-specific captions | FALSE
TSK-033 | 2 | Check brand voice | FALSE
TSK-033 | 3 | Confirm #ThinkVisually where appropriate and no emoji | FALSE
TSK-034 | 1 | Create thumbnails | FALSE
TSK-034 | 2 | Create quote cards | FALSE
TSK-034 | 3 | Create carousel assets | FALSE
TSK-034 | 4 | Verify CMYK palette and registration-mark motif | FALSE
TSK-035 | 1 | Schedule on gholmesdesigns.com | FALSE
TSK-036 | 1 | Queue platform posts | FALSE
TSK-037 | 1 | Link social copy to blog or video | FALSE
TSK-037 | 2 | Link blog to video | FALSE
TSK-038 | 1 | Verify approved typefaces and palette | FALSE
TSK-038 | 2 | Confirm no gradients or mascots | FALSE
TSK-038 | 3 | Confirm no visual clichés | FALSE
TSK-039 | 1 | Pull prior-week native analytics | FALSE
TSK-040 | 1 | Record topic, hook, and format for next brief | FALSE
TSK-041 | 1 | Draft | FALSE
TSK-041 | 2 | Edit | FALSE
TSK-041 | 3 | Deliver as Markdown | FALSE
TSK-042 | 1 | Script | FALSE
TSK-042 | 2 | Storyboard | FALSE
TSK-042 | 3 | InstaDoodle illustration | FALSE
TSK-042 | 4 | Animation | FALSE
TSK-043 | 1 | Draft platform-specific captions | FALSE
TSK-043 | 2 | Check brand voice | FALSE
TSK-043 | 3 | Confirm #ThinkVisually where appropriate and no emoji | FALSE
TSK-044 | 1 | Create thumbnails | FALSE
TSK-044 | 2 | Create quote cards | FALSE
TSK-044 | 3 | Create carousel assets | FALSE
TSK-044 | 4 | Verify CMYK palette and registration-mark motif | FALSE
TSK-045 | 1 | Schedule on gholmesdesigns.com | FALSE
TSK-046 | 1 | Queue platform posts | FALSE
TSK-047 | 1 | Link social copy to blog or video | FALSE
TSK-047 | 2 | Link blog to video | FALSE
TSK-048 | 1 | Verify approved typefaces and palette | FALSE
TSK-048 | 2 | Confirm no gradients or mascots | FALSE
TSK-048 | 3 | Confirm no visual clichés | FALSE
TSK-049 | 1 | Pull prior-week native analytics | FALSE
TSK-050 | 1 | Record topic, hook, and format for next brief | FALSE
TSK-051 | 1 | Draft | FALSE
TSK-051 | 2 | Edit | FALSE
TSK-051 | 3 | Deliver as Markdown | FALSE
TSK-052 | 1 | Script | FALSE
TSK-052 | 2 | Storyboard | FALSE
TSK-052 | 3 | InstaDoodle illustration | FALSE
TSK-052 | 4 | Animation | FALSE
TSK-053 | 1 | Draft platform-specific captions | FALSE
TSK-053 | 2 | Check brand voice | FALSE
TSK-053 | 3 | Confirm #ThinkVisually where appropriate and no emoji | FALSE
TSK-054 | 1 | Create thumbnails | FALSE
TSK-054 | 2 | Create quote cards | FALSE
TSK-054 | 3 | Create carousel assets | FALSE
TSK-054 | 4 | Verify CMYK palette and registration-mark motif | FALSE
TSK-055 | 1 | Schedule on gholmesdesigns.com | FALSE
TSK-056 | 1 | Queue platform posts | FALSE
TSK-057 | 1 | Link social copy to blog or video | FALSE
TSK-057 | 2 | Link blog to video | FALSE
TSK-058 | 1 | Verify approved typefaces and palette | FALSE
TSK-058 | 2 | Confirm no gradients or mascots | FALSE
TSK-058 | 3 | Confirm no visual clichés | FALSE
TSK-059 | 1 | Pull prior-week native analytics | FALSE
TSK-060 | 1 | Record final learnings and next-campaign recommendations | FALSE
TSK-101 | 1 | Remove 1,200+ miles/day claim | TRUE
TSK-101 | 2 | Remove 100+ customers claim | TRUE
TSK-101 | 3 | Use thousands of miles each month | TRUE
TSK-101 | 4 | Update closing tagline | TRUE
TSK-101 | 5 | Use Community Brand Ambassadors terminology | TRUE
TSK-101 | 6 | Update CTA to Get your campaign moving | TRUE
TSK-102 | 1 | Confirm driver inquiry collection | TRUE
TSK-102 | 2 | Confirm brand inquiry collection | TRUE
TSK-103 | 1 | Launch ads | TRUE
TSK-103 | 2 | Confirm inquiry routing | FALSE
TSK-104 | 1 | Generate weekly blog draft | FALSE
TSK-104 | 2 | Generate weekly social draft | FALSE
TSK-104 | 3 | Route to Garnie for review | FALSE

## Dependencies
task_key | prerequisite_task_key
TSK-005 | TSK-001
TSK-006 | TSK-003
TSK-007 | TSK-001
TSK-007 | TSK-002
TSK-015 | TSK-011
TSK-016 | TSK-013
TSK-017 | TSK-011
TSK-017 | TSK-012
TSK-025 | TSK-021
TSK-026 | TSK-023
TSK-027 | TSK-021
TSK-027 | TSK-022
TSK-035 | TSK-031
TSK-036 | TSK-033
TSK-037 | TSK-031
TSK-037 | TSK-032
TSK-045 | TSK-041
TSK-046 | TSK-043
TSK-047 | TSK-041
TSK-047 | TSK-042
TSK-055 | TSK-051
TSK-056 | TSK-053
TSK-057 | TSK-051
TSK-057 | TSK-052
TSK-103 | TSK-102

## DataDictionary
Sheet | Column | App / import target | Required | Type / format | Allowed value or default | Rules
Clients | client_key | Workbook reference only | Yes | Text | — | Unique in Clients; key pattern and length from README.
Clients | name | clients.name | Yes | Text | — | Trimmed; 2–120 characters; conflict key is case-insensitive name.
Clients | contact_name | clients.contact_name | No | Text | Blank → null | Trim surrounding whitespace.
Clients | email | clients.email | No | Email | Blank → null | Must be a valid email when present.
Clients | phone | clients.phone | No | Text | Blank → null | Preserve punctuation and leading plus sign.
Clients | website | clients.website | No | URL | Blank → null | Absolute URL when present.
Clients | notes | clients.notes | No | Text | Blank → null | Literal text only.
Clients | client_import_source | client_import_aliases.source_namespace | No | UUID text | Blank → no identity | Optional; supply with client_import_id. Namespace is campaign-playbook:<uuid>.
Clients | client_import_id | client_import_aliases.external_id | No | Text | Blank → no identity | The client's id at that source, matched exactly. An identity match wins over the name.
Projects | project_key | Workbook reference only | Yes | Text | — | Unique in Projects.
Projects | client_key | projects.client_id resolver | Yes | Key reference | — | Must resolve to Clients.client_key.
Projects | name | projects.name | Yes | Text | — | Trimmed; 2–160 characters; conflict key is client plus name.
Projects | status | projects.status | No | Enum | ACTIVE | PLANNING, ACTIVE, ON_HOLD, COMPLETE.
Projects | priority | projects.priority | No | Enum | MEDIUM | LOW, MEDIUM, HIGH, URGENT.
Projects | start_date | projects.start_date | No | YYYY-MM-DD text | Blank → null | Must be a real calendar date.
Projects | target_deadline | projects.target_deadline | No | YYYY-MM-DD text | Blank → null | Must be a real calendar date; must not precede start_date.
Projects | description | projects.description | No | Text | Blank → null | Literal text only.
Projects | notes | projects.notes | No | Text | Blank → null | Literal text only.
Projects | position | projects.position | No | Positive integer | Next position | One-based in workbook; normalized to zero-based storage.
Tasks | task_key | Workbook reference only | Yes | Text | — | Unique in Tasks.
Tasks | project_key | tasks.project_id resolver | Yes | Key reference | — | Must resolve to Projects.project_key.
Tasks | title | tasks.title | Yes | Text | — | Trimmed; 2–200 characters; conflict key is project plus title.
Tasks | task_type | tasks.task_type | No | Enum | Blank → null | Use exact task-type value from AllowedValues.
Tasks | status | tasks.status | No | Enum | BACKLOG | BACKLOG, TODO, IN_PROGRESS, REVIEW, COMPLETE.
Tasks | priority | tasks.priority | No | Enum | MEDIUM | LOW, MEDIUM, HIGH, URGENT.
Tasks | start_date | tasks.start_date | No | YYYY-MM-DD text | Blank → null | Must be a real calendar date.
Tasks | due_date | tasks.due_date | No | YYYY-MM-DD text | Blank → null | Must be a real calendar date; must not precede start_date.
Tasks | description | tasks.description | No | Text | Blank → null | Literal text only.
Tasks | notes | tasks.notes | No | Text | Blank → null | Literal text only.
Tasks | position | tasks.position | No | Positive integer | Next position | One-based per project and status; normalized to zero-based storage.
ChecklistItems | task_key | checklist_items.task_id resolver | Yes | Key reference | — | Must resolve to Tasks.task_key.
ChecklistItems | item_order | checklist_items.position | Yes | Positive integer | — | One-based per task; duplicates rejected; normalized to zero-based storage.
ChecklistItems | title | checklist_items.text | Yes | Text | — | Trimmed and non-empty.
ChecklistItems | completed | checklist_items.completed | No | Boolean | FALSE | Native TRUE/FALSE value; not quoted text.
Dependencies | task_key | task_dependencies.task_id resolver | Yes* | Key reference | — | Required when a Dependencies row is present; must resolve to Tasks.
Dependencies | prerequisite_task_key | task_dependencies.dependency_id resolver | Yes* | Key reference | — | Must resolve to Tasks; cannot equal task_key.

## AllowedValues
Field | Allowed value | Meaning / import behavior
schema_version | 1 | Current format version; unsupported versions are rejected.
Projects.status | PLANNING | Project is being planned.
Projects.status | ACTIVE | Project is active.
Projects.status | ON_HOLD | Project is paused.
Projects.status | COMPLETE | Project is complete.
Tasks.status | BACKLOG | Unscheduled work.
Tasks.status | TODO | Ready to start.
Tasks.status | IN_PROGRESS | Work has started.
Tasks.status | REVIEW | Awaiting review.
Tasks.status | COMPLETE | Finished; completed_at becomes confirmation timestamp.
priority | LOW | Lowest urgency.
priority | MEDIUM | Normal default.
priority | HIGH | High urgency.
priority | URGENT | Highest urgency.
task_type | BLOG_POST | Blog content.
task_type | VIDEO | Video work.
task_type | SOCIAL_POST | Social content.
task_type | GRAPHICS | Graphics production.
task_type | SCHEDULING | Scheduling and publishing.
task_type | QA_BRAND_PASS | Brand quality review.
task_type | ADMIN | Administrative and reporting work.
task_type | OTHER | Work outside the defined categories.
ChecklistItems.completed | FALSE | Initial item is incomplete.
ChecklistItems.completed | TRUE | Initial item is complete.